## Bug_report_Admin
Bug ID | Bug Title | Module Name | Description | Steps to Reproduce | Expected Result | Actual Result | Test_Data | Severity | Priority | Environment | Status | Date
BUG-001 | Missing of Day/Night mode button | Dashboard | Day/night mode button is not visible or missing in the dashboard | 1) Go to Login page 2) Enter admin user email 3) Enter admin user password 4) Redirect to Dashboard | Mode button should be visible at the right hand top side of the application | Button is not visible | email: admin@gmail.com password:admin@123 | Low | Low | Web (Edge Browser) | Not fixed | 2026-04-07
BUG-002 | Payment Failed | Shop Owners | Payment intiation failed in all the billing cycles | 1) Login as Admin User 2) Click on Add Shop Owner 3) Provide phone number and click on next button 4) Choose/select payment plan and click on proceed button | Redirects to payment page | Error message displayed as "Failed to intitate payment" | N/A | High | High | Web (Edge Browser) | Not fixed | 2026-04-07
BUG-003 | Success message is not displayed | Shop Owners | Notification message is not displayed after deletion of Shop owner info | 1) Login as Admin User 2) Go to Shop Owners 3) Click on delete button of any entry 4) Click on delete button to Confirm | Success message should be displayed on screen | Success message is not displayed | N/A | Low | Medium | Web (Edge Browser) | Not fixed | 2026-04-07
BUG-004 | Invalid characters are accepted | Sales Agents | Numeric values are accepted in the name field | 1) Login as Admin User 2) Go to Sales Agents 3) Click on edit button on selected entry 4) Provide numeric values and click on Update button | Error or validation message displays to provide valid name | No display of error message and updates the entry successfully | Full Name: 8495309 email: user@example.com | Low | Medium | Web (Edge Browser) | Not fixed | 2026-04-07
BUG-005 | Invalid Data is accepted | User management | Invalid user data accepted while creating the New Admin User | 1) Login as Admin User 2) Go to User management 3) Click on Add button 4) Provide invalid user data in all the fields | Validation message displays on screen and system doesn't save the info | System updated the details succesfully without displaying any error message | Name: 79809-09 Email: wddssdas Phone: 88256 | High | High | Web (Edge Browser) | Not fixed | 2026-04-07
BUG-006 | Invalid characters are accepted | Subscription plans | Numeric values are accepted in the name field | 1) Login as Admin User 2) Go to Subscription plans 3) Click on edit button on selected plan 4) Provide numeric values in the name field and fill all the mandatory fields with valid data 5) Click on Update button | Error or validation message displays to provide valid name | No display of error message and updates the entry successfully | Plan Name: 87978 Plan Code: 353536 monthly price: 1 quarterly price: 2799 yearly price: 9999 max stores:1 | Low | Medium | Web (Edge Browser) | Not fixed | 2026-04-07
BUG-007 | Deletion of Active plan | Subscription plans | Admin user is able to delete the Active subscription plan which is in Use | 1) Login as Admin User 2) Go to Subscription plans 3) Click on Delete button on selected Active plan | Subscription plan is displayed successfully | Admin can not delete the Active user plan System should display confirm delete pop-up before deleting directly | N/A | High | High | Web (Edge Browser) | Not fixed | 2026-04-07
BUG-008 | Ignores Character Limitation | Sales Agents | Character limitation message is not displayed and invalid data is accepted | 1) Login as Admin User 2) Go to Sales Agents 3) Click on edit button on selected entry 4) Provide invalid data and click on Update button | Error or validation message displays to provide valid name | System saved the details instead of raising the error message | Full Name: bv bnb n jnjknjnbjnjnnnnjnnnjjjjjjjkjnjknEFEDMKLMJLO5269295223263 email: testuser_2@gmail.com Phone Number: 8559777625 Commission Percentage (%): 2 Status: Active | Low | Medium | Web (Edge Browser) | Not fixed | 2026-04-07
BUG-009
BUG-010
BUG-011