## Bug_report_Admin
Bug ID | Bug Title | Module Name | Description | Steps to Reproduce | Expected Result | Actual Result | Test_Data | Severity | Priority | Environment | Status | Date
BUG-001 | Dashboard Guide Not Loading | Dashboard | "How to Use" button opens new tab, but dashboard guide fails to load/appear after login. | 1) Login using valid credentials 2) Verify Page redirects to Dashboard 3) Click the "How to Use" guide button. | The dashboard guide should appear fully in the new tab. | A new tab opens, but the dashboard guide is not visible or fails to load. | Email: bhargavi.k.visys@gmail.com Password: Owner@123 Shop Owner ID: owner_1196 | Low | Medium | Web Browser (Firefox) | Not fixed | 2026-04-08
BUG-002 | No Character Limit on Store Fields | My Stores | System allows infinite characters in Store Name and City fields without restriction or validation error, despite expected limits. | 1 Login with valid credentials. 2) Go to My Stores. 3) Click Add Store button. 4) Enter long invalid data: Store Name and City fields 5) Click Create button. | Restrict characters and show validation error message. | No restriction; infinite characters accepted, no validation error on exceed | Store Name: BKJHFRNLKLSDFM NDRFNKMFES N K KFEWLKMFEASMKLFESN JLCSFKMAFKF City: FEFDVDF DFEFSEFfeafaafefafagsedgedgvaedvfadfc | Low | Low | Web Browser (Firefox) | Not fixed | 2026-04-08
BUG-003 | Discount Rule Not Creating | Discount Rule | New discount rule fails to save/create despite filling mandatory fields; invalid error appears instead of success | 1) Login with valid credentials. 2) Go to Discount Rule > Click Create New button. 3) Select Store: Click Deal of the Day 4) Fill all mandatory fields (e.g., Name: Clearance Sale, Min:500, Max:2000, Customer:5%, Dates:08/04/2026 05:30pm-09/04/2026 11:59pm). 5) Click Create button. | Rule creates successfully and lists in Rules dashboard. | Rule not created; invalid error message on screen (should appear in Rules dashboard) | Select Store: Click: Deal of the Day Discount Rule Name: Clearance Sale Min amount: 500 Max amount: 2000 Customer limit: 5 Option 1: 5% Start Date: 08/04/2026 05:30 pm End Date: 09/04/2026 11:59 pm | High | High | Web Browser (Firefox) | Not fixed | 2026-04-08
BUG-004 | [9 empty] | Web Browser (Firefox) | Not fixed | 2026-04-08
BUG-005 | [9 empty] | Web Browser (Firefox) | Not fixed | 2026-04-08
BUG-006 | [9 empty] | Web Browser (Firefox) | Not fixed | 2026-04-08
BUG-007 | [9 empty] | Web Browser (Firefox) | Not fixed | 2026-04-08
BUG-008 | [9 empty] | Web Browser (Firefox) | Not fixed | 2026-04-08
BUG-009
BUG-010
BUG-011